## Dashboard
DIY retailer sustainability review
Portfolio demonstration. 2025 operating data for one fictional store and five sample products.
Review date |  | 2026-09-27 |  | Amber cells are inputs. Pale green cells contain calculations.
Supplier evidence readiness |  |  |  | High-priority suppliers | Overdue actions
0% |  |  |  | 3 | 0
Current claim evidence, 5 suppliers |  |  |  | Evidence gaps needing attention | Based on the review date
Store waste recycled |  |  |  | Packaging sold in 2025 | Planned resource cost
69.62% |  |  |  | 3132 | 3806
2025 weighted annual rate |  |  |  | Sample products; estimated kg | Includes staff time and contingency
Action priority | Open | Overdue | Closed | 2025 energy-related CO2 estimates
High | 7 | 0 | 0 | Electricity consumption (tonnes CO2) |  | 25.9711
Medium | 6 | 0 | 0 | Natural gas combustion (tonnes CO2) |  | 19.9097
Low | 0 | 0 | 0
CO2-only estimates. Electricity includes losses and excludes emissions outside Ireland. These results are not a complete Scope 1 and Scope 2 inventory.
Evidence remains unverified even when input fields are complete.
The data is synthetic. This workbook supports evidence collection, review and planning; it does not certify supplier or legal compliance.

## Actions
Action_ID | Topic | Linked_ID | Action | Internal_Owner | Priority | Start_Date | Due_Date | Status | Completion_Date | Closure_Evidence | Due_Status | Days_Overdue | Closure_Check | Data_Type | Action metrics | Value
ACT001 | Supplier evidence | SUP001 | Request sourcing certificate and documents linking it to the supplied timber | Garden Category Manager | High | 2026-09-28 | 2026-10-12 | Awaiting response |  |  | Scheduled | 0 | Open | Synthetic | Total actions | 13
ACT002 | Supplier evidence | SUP002 | Check the stated VOC content and which paint products the document covers | Paint Category Manager | Medium | 2026-09-28 | 2026-10-12 | Under review |  |  | Scheduled | 0 | Open | Synthetic | Closed with evidence | 0
ACT003 | Supplier evidence | SUP003 | Request model-specific energy performance evidence and check it against the claim | Lighting Category Manager | Medium | 2026-09-28 | 2026-10-12 | Awaiting response |  |  | Scheduled | 0 | Open | Synthetic | Open actions | 13
ACT004 | Supplier evidence | SUP004 | Request evidence supporting the 80% recycled-content claim, confirm which packaging components it covers, and ask where the recycled material is sourced. | Tools Category Manager | High | 2026-09-28 | 2026-10-12 | Awaiting response |  |  | Scheduled | 0 | Open | Synthetic | Overdue | 0
ACT005 | Supplier evidence | SUP005 | Request a current certificate and check that it covers the relevant supplier and timber products | Garden Category Manager | High | 2026-09-28 | 2026-10-12 | Awaiting response |  |  | Scheduled | 0 | Open | Synthetic | Due soon or today | 1
ACT006 | Packaging data | All components | Obtain measured component weights and linked evidence. | Commercial and Suppliers | Medium | 2026-09-28 | 2026-10-16 | Not started |  |  | Scheduled | 0 | Open | Synthetic | Closure incomplete | 0
ACT007 | Claims review | REG001 | Review public claim wording and record approval or withdrawal. | Commercial and Marketing | High | 2026-09-27 | 2026-09-30 | Not started |  |  | Due soon | 0 | Open | Synthetic
ACT008 | Timber screening | REG003 | Confirm product codes, retailer role, size and timber traceability requirements. | Sustainability Manager | High | 2026-09-28 | 2026-10-09 | Not started |  |  | Scheduled | 0 | Open | Synthetic
ACT009 | Activity evidence | STORE01 | Replace demo activity data with bills and waste records in a real deployment. | Operations and Finance | Medium | 2026-09-28 | 2026-10-23 | Not started |  |  | Scheduled | 0 | Open | Synthetic | ACT001 to ACT005 link to Suppliers. Edit the supplier status there. Other task dates and owners are planning assumptions. A Closed status needs both a completion date and a closure reference.
ACT010 | GHG boundary | STORE01 | Define the full inventory boundary, other gases and the electricity method. | Sustainability Manager | Medium | 2026-09-28 | 2026-10-23 | Not started |  |  | Scheduled | 0 | Open | Synthetic
ACT011 | WEEE review | REG006 | Check electrical producer registration, take-back arrangements and records. | Operations Manager | High | 2026-09-28 | 2026-10-02 | Not started |  |  | Scheduled | 0 | Open | Synthetic
ACT012 | Lighting scope | REG005 | Confirm light-source classification and the applicable label and model data. | Lighting Category Manager | Medium | 2026-09-28 | 2026-10-09 | Not started |  |  | Scheduled | 0 | Open | Synthetic
ACT013 | Packaging scope | REG002 | Map PPWR duties, phased dates and Irish producer-responsibility requirements. | Sustainability Manager | High | 2026-09-28 | 2026-10-02 | Not started |  |  | Scheduled | 0 | Open | Synthetic
Formulas:
Start_Date = XLOOKUP([Linked_ID], Suppliers!$A2:A501, Suppliers!$K2:K501, "Check supplier ID")
Due_Date = XLOOKUP([Linked_ID], Suppliers!$A2:A501, Suppliers!$L2:L501, "Check supplier ID")

## Suppliers
Supplier_ID | Supplier_Name | Supplier_Country | Main_Category | Internal_Owner | Data_Type | Sustainability_Claim | Evidence_Status | Verification_Status | Next_Action | Request_Date | Due_Date | Follow_Up_Status | Evidence_Reference | Review_Notes | Due_Status | Priority | Priority_Reason | Claim_Use_Status | Supplier metrics | Value
SUP001 | Demo Timber Ltd | Ireland | Timber & Garden | Garden Category Manager | Synthetic | Timber comes from responsibly managed forests | Not received | Unverified | Request sourcing certificate and documents linking it to the supplied timber | 2026-09-28 | 2026-10-12 | Awaiting response | Not provided | Sourcing claim cannot be checked until supporting evidence is received | Scheduled | High | Sourcing claim has no supporting evidence. | Hold claim | Suppliers | 5
SUP002 | Demo Paint Palace Ltd | India | Paint | Paint Category Manager | Synthetic | Paint has low VOC content | Technical data sheet received; review pending | Unverified | Check the stated VOC content and which paint products the document covers | 2026-09-28 | 2026-10-12 | Under review | Demo document pending | Technical data sheet needs review for VOC content and product coverage |  | Medium | Technical document is recorded as received but still needs review. | Hold claim | Evidence ready | 0
SUP003 | Demo Lighting Solutions Ltd | China | Lighting | Lighting Category Manager | Synthetic | Lighting products are energy-efficient | Product specifications received; review pending | Unverified | Request model-specific energy performance evidence and check it against the claim | 2026-09-28 | 2026-10-12 | Awaiting response | Demo document pending | Specifications need review for model-specific energy performance | Scheduled | Medium | Model-specific performance still needs checking. | Hold claim | Evidence readiness | 0%
SUP004 | Demo EverydayTools Ltd | China | Tools | Tools Category Manager | Synthetic | Tool packaging contains 80% recycled material | Supplier statement received; supporting evidence missing | Unverified | Request evidence supporting the 80% recycled-content claim, confirm which packaging components it covers, and ask where the recycled material is sourced. | 2026-09-28 | 2026-10-12 | Awaiting response | Demo document pending | Supplier statement does not substantiate 80%; percentage, components and material source need checking | Scheduled | High | The 80% claim has no proof of percentage, components or source. | Hold claim | High priority | 3
SUP005 | Demo Garden King Ltd | Ireland | Garden Furniture | Garden Category Manager | Synthetic | Timber is eco-friendly | Expired certificate | Unverified | Request a current certificate and check that it covers the relevant supplier and timber products | 2026-09-28 | 2026-10-12 | Awaiting response | Demo document pending | Certificate has expired; request current evidence and check product coverage | Scheduled | High | Certificate has expired and the environmental claim is broad. | Hold claim | Unverified claims | 5
[19 empty] | Expired certificates | 1
[19 empty] | Response overdue | 0
Priority is a project judgement about evidence gaps. It is not a legal risk score. Ready for approval still requires a claim wording and product scope decision.

## Products
Product_ID | Supplier_ID | Product_Name | Category | Units_Sold_2025 | Data_Type | Supplier_Name | Supplier_Link_Status | Product metrics | Value
PR001 | SUP001 | Timber fence panel | Timber & Garden | 1200 | Synthetic | Demo Timber Ltd | Linked | Sample products | 5
PR002 | SUP002 | Interior paint 5L | Paint | 5000 | Synthetic | Demo Paint Palace Ltd | Linked | Units sold in 2025 | 12000
PR003 | SUP003 | LED ceiling light | Lighting | 3000 | Synthetic | Demo Lighting Solutions Ltd | Linked
PR004 | SUP004 | 20-piece tool set | Tools | 2000 | Synthetic | Demo EverydayTools Ltd | Linked
PR005 | SUP005 | Wooden garden chair | Garden Furniture | 800 | Synthetic | Demo Garden King Ltd | Linked | The five products are a sample. Their volumes do not establish entity-wide packaging obligations or company turnover.

## Packaging
Packaging_ID | Product_ID | Component | Material | Estimated_Weight_g_Per_Unit | Evidence_Status | Data_Type | Units_Sold_2025 | Annual_Packaging_kg | Verified_Recycled_Content | Recycled_Material_Source | Recycled_Evidence_Reference | Recycled_Verification | Weight_Record_Status | Weight_Evidence_Reference | Packaging metrics | Value
PK001 | PR001 | Protective film | Plastic | 60 | Not provided | Synthetic | 1200 | 72 |  | Not provided | Not provided | Unverified | Complete | Not provided | Component records | 8
PK002 | PR002 | Paint tub | Plastic | 250 | Not provided | Synthetic | 5000 | 1250 |  | Not provided | Not provided | Unverified | Complete | Not provided | Complete weight records | 8
PK003 | PR002 | Tub lid | Plastic | 50 | Not provided | Synthetic | 5000 | 250 |  | Not provided | Not provided | Unverified | Complete | Not provided | Weight data completion | 100%
PK004 | PR003 | Outer box | Cardboard | 120 | Not provided | Synthetic | 3000 | 360 |  | Not provided | Not provided | Unverified | Complete | Not provided | Verified weight records | 0
PK005 | PR004 | Outer box | Cardboard | 180 | Not provided | Synthetic | 2000 | 360 |  | Not provided | Not provided | Unverified | Complete | Not provided | Annual packaging kg | 3132
PK006 | PR004 | Protective insert | Plastic | 20 | Not provided | Synthetic | 2000 | 40 |  | Not provided | Not provided | Unverified | Complete | Not provided | Verified recycled records | 0
PK007 | PR005 | Outer box | Cardboard | 900 | Not provided | Synthetic | 800 | 720 |  | Not provided | Not provided | Unverified | Complete | Not provided
PK008 | PR005 | Protective film | Plastic | 100 | Not provided | Synthetic | 800 | 80 |  | Not provided | Not provided | Unverified | Complete | Not provided
[15 empty] | Material | Annual kg | Chart zero baseline
[15 empty] | Plastic | 1692 | 0
[15 empty] | Cardboard | 1440 | 0
The 80% tools-packaging claim remains in Suppliers. No percentage is assigned to an individual component until its coverage, material source and supporting evidence are confirmed. Blank verified percentages mean unknown, not zero.

## ESG_Monthly
Month | Site_ID | Electricity_kWh | Gas_kWh_GCV | Total_Waste_kg | Recycled_Waste_kg | Data_Type | Electricity_CO2_kg | Gas_CO2_kg | Recycling_Rate | Record_Status | Factor | kg_CO2_per_kWh | Year | Status | Source_URL | Month | Electricity CO2 kg | Gas CO2 kg
2025-01-01 | STORE01 | 12000 | 18000 | 1200 | 720 | Synthetic | 2373.6 | 3303 | 60% | Complete | Electricity consumption | 0.1978 | 2025 | Provisional | https://www.seai.ie/data-and-insights/seai-statistics/conversion-factors | Jan | 2373.6 | 3303
2025-02-01 | STORE01 | 11200 | 16000 | 1100 | 682 | Synthetic | 2215.36 | 2936 | 62% | Complete | Natural gas GCV | 0.1835 | 2025 | Provisional | https://www.seai.ie/data-and-insights/seai-statistics/conversion-factors | Feb | 2215.36 | 2936
2025-03-01 | STORE01 | 10800 | 13000 | 1300 | 819 | Synthetic | 2136.24 | 2385.5 | 63% | Complete | [5 empty] | Mar | 2136.24 | 2385.5
2025-04-01 | STORE01 | 10200 | 9000 | 1500 | 975 | Synthetic | 2017.56 | 1651.5 | 65% | Complete | Source | https://www.seai.ie/data-and-insights/seai-statistics/conversion-factors |  |  |  | Apr | 2017.56 | 1651.5
2025-05-01 | STORE01 | 10000 | 5000 | 1600 | 1072 | Synthetic | 1978 | 917.5 | 67% | Complete | [5 empty] | May | 1978 | 917.5
2025-06-01 | STORE01 | 9800 | 2500 | 1700 | 1173 | Synthetic | 1938.44 | 458.75 | 69% | Complete | CO2 estimates only. Electricity includes network losses and excludes emissions arising outside Ireland. The factor covers more than Scope 2 alone. A complete Scope 1 and Scope 2 CO2e inventory remains pending. |  |  |  |  | Jun | 1938.44 | 458.75
2025-07-01 | STORE01 | 10000 | 1500 | 1800 | 1260 | Synthetic | 1978 | 275.25 | 70% | Complete | [5 empty] | Jul | 1978 | 275.25
2025-08-01 | STORE01 | 10100 | 1500 | 1750 | 1260 | Synthetic | 1997.78 | 275.25 | 72% | Complete | [5 empty] | Aug | 1997.78 | 275.25
2025-09-01 | STORE01 | 10600 | 4000 | 1500 | 1095 | Synthetic | 2096.68 | 734 | 73% | Complete | [5 empty] | Sep | 2096.68 | 734
2025-10-01 | STORE01 | 11400 | 8000 | 1400 | 1036 | Synthetic | 2254.92 | 1468 | 74% | Complete | Gas inputs use GCV. These activity inputs are synthetic and have no bills or waste transfer records attached. The waste figures describe store waste, not packaging sold with products. |  |  |  |  | Oct | 2254.92 | 1468
2025-11-01 | STORE01 | 12200 | 13000 | 1500 | 1140 | Synthetic | 2413.16 | 2385.5 | 76% | Complete | [5 empty] | Nov | 2413.16 | 2385.5
2025-12-01 | STORE01 | 13000 | 17000 | 1800 | 1404 | Synthetic | 2571.4 | 3119.5 | 78% | Complete | [5 empty] | Dec | 2571.4 | 3119.5
Annual Total |  | 131300 | 108500 | 18150 | 12636 |  | 25971.14 | 19909.75 | 69.62%
[11 empty] | Factors checked on | 2026-09-27

## Regulations
Regulation_ID | Topic | Framework | Applicability_to_Demo | Milestone_Type | Application_Date | Internal_Owner | Required_Action | Readiness_Status | Action_ID | Source | Source_URL | Checked_On | Next_Source_Review | Date_Status | Days_to_Application | Scope_Notes | Register scope | Value
REG001 | Environmental claims | S.I. 124/2026 and Directive (EU) 2024/825 | Relevant to consumer-facing sustainability claims. | Application date | 2026-09-27 | Commercial and Marketing | Review claim wording and hold unsupported claims. | Not assessed | ACT007 | CCPC | https://www.ccpc.ie/information-for-businesses/guidance-for-businesses/consumer-protection-guidance/european-union-(empowering-consumers-for-the-green-transition)-regulations-2026 | 2026-09-27 | 2026-10-27 | Application date reached | 0 | Evidence alone does not make a broad claim acceptable. Obtain a wording review. | Topics covered | 6
REG002 | Packaging requirements | Regulation (EU) 2025/40 | Packaged goods are relevant. Confirm the retailer role and individual duties. | General application | 2026-08-12 | Sustainability Manager | Map relevant requirements and build component-level evidence. | Not assessed | ACT013 | European Commission | https://environment.ec.europa.eu/news/new-eu-rules-packaging-enter-application-2026-08-11_en | 2026-09-27 | 2026-10-27 | Application date reached | 0 | Implementation is phased. The general application date is not the start date of every labelling or recycled-content requirement. | Not assessed | 6
REG003 | Deforestation and timber | Regulation (EU) 2023/1115 as amended | Screen timber panel and wooden chair by commodity code, role and business size. | Conditional application | 2026-12-30 | Commercial and Sustainability | Confirm scope, traceability needs and the applicable start date. | Not assessed | ACT008 | European Commission | https://environment.ec.europa.eu/topics/forests/deforestation/regulation-deforestation-free-products_en | 2026-09-27 | 2026-10-27 | Upcoming | 94 | 30-Dec-2026 applies to large/medium operators and small/micro operators already under EUTR. Other small/micro operators: 30-Jun-2027. A sourcing certificate alone is insufficient. | Source checks due | 0
REG004 | Paint VOC content | S.I. 564/2012 as amended | Screen the paint product category and its specific VOC limit. | Ongoing obligation |  | Paint Category Manager | Check technical sheet, product category and VOC labelling. | Not assessed | ACT002 | EPA | https://www.epa.ie/our-services/compliance--enforcement/air/decorative-paints/decorative-paints-regulations/ | 2026-09-27 | 2026-10-27 | Ongoing |  | Low VOC is a claim. The legal limit depends on the paint category; do not use one universal threshold.
REG005 | Lighting information | Regulation (EU) 2019/2015 | Confirm whether the product is a light source or a containing product. | Ongoing obligation |  | Lighting Category Manager | Check model classification, applicable label and product information. | Not assessed | ACT012 | SEAI | https://www.seai.ie/plan-your-energy-journey/for-your-business/energy-efficient-products/energy-tyre-labelling-and-ecodesign/lighting-products | 2026-09-27 | 2026-10-27 | Ongoing |  | Check EPREL and supplier model references where applicable. Energy labelling and ecodesign duties differ by role. | Focused screening register for the sample products. Internal task due dates are in Actions. No legal-compliance conclusion is made from a completed task.
REG006 | Electrical waste take-back | Irish WEEE obligations | Relevant to the lighting product. Check importer as well as retailer duties. | Ongoing obligation |  | Operations Manager | Check producer registration, take-back notices and collection records. | Not assessed | ACT011 | EPA | https://www.epa.ie/our-services/compliance--enforcement/waste/weee/information-for-distributors-of-eee-and-batteries/ | 2026-09-27 | 2026-10-27 | Ongoing |  | Retailer duties include take-back and record keeping. Confirm the precise product and sales-channel requirements.

## Costs
Cost_ID | Action_ID | Cost_Item | Cost_Type | Quantity | Unit | Rate_EUR | Base_Cost_EUR | Contingency_Rate | Contingency_EUR | Planned_Cost_EUR | Actual_Cost_EUR | Variance_EUR | Estimate_Basis | Internal_Owner | Cost assumptions | Value
C001 | ACT001 | Supplier evidence review | Staff time | 10 | hours | 35 | 350 | 10% | 35 | 385 |  |  | Synthetic planning allowance; no supplier quote. | Garden Category Manager | Contingency allowance | 10%
C002 | ACT006 | Packaging measurement | Staff time | 8 | hours | 30 | 240 | 10% | 24 | 264 |  |  | Synthetic planning allowance; no supplier quote. | Commercial and Suppliers | Resource cost incl. contingency | 3806
C003 | ACT007 | Environmental claim review | Staff time | 8 | hours | 60 | 480 | 10% | 48 | 528 |  |  | Synthetic planning allowance; no supplier quote. | Commercial and Marketing | Staff time incl. contingency | 3674
C004 | ACT008 | Timber scope and traceability review | Staff time | 12 | hours | 45 | 540 | 10% | 54 | 594 |  |  | Synthetic planning allowance; no supplier quote. | Sustainability Manager | Equipment incl. contingency | 132
C005 | ACT009 | Activity data reconciliation | Staff time | 6 | hours | 35 | 210 | 10% | 21 | 231 |  |  | Synthetic planning allowance; no supplier quote. | Operations and Finance | Actual amounts entered | 0
C006 | ACT010 | GHG inventory boundary review | Staff time | 8 | hours | 60 | 480 | 10% | 48 | 528 |  |  | Synthetic planning allowance; no supplier quote. | Sustainability Manager
C007 | ACT011 | WEEE procedure review | Staff time | 4 | hours | 35 | 140 | 10% | 14 | 154 |  |  | Synthetic planning allowance; no supplier quote. | Operations Manager
C008 | ACT012 | Lighting model review | Staff time | 4 | hours | 45 | 180 | 10% | 18 | 198 |  |  | Synthetic planning allowance; no supplier quote. | Lighting Category Manager | Staff time is an opportunity-cost allowance, not automatically additional cash spend. Equipment is a planning estimate. VAT, scheme fees, fines and mandatory tariffs are not modelled. Blank actuals mean unknown. No expenditure has been approved.
C009 | ACT013 | Packaging obligations review | Staff time | 12 | hours | 60 | 720 | 10% | 72 | 792 |  |  | Synthetic planning allowance; no supplier quote. | Sustainability Manager
C010 | ACT006 | Packaging weighing scale | Equipment | 1 | item | 120 | 120 | 10% | 12 | 132 |  |  | Synthetic planning allowance; no supplier quote. | Commercial and Suppliers
|  | Total resource cost |  |  |  |  | 3460 |  | 346 | 3806 | Not complete

## README
About this project
Purpose | Build a sustainability readiness system for a fictional Irish DIY retailer. Track supplier evidence, products, packaging, environmental KPIs, regulatory topics, costs and corrective actions.
Owner | Sagar Malik. Portfolio demonstration inspired by the green colour direction of Woodie's. It is not a Woodie's operational workbook or an official brand template.
Data boundary | Five suppliers, five products, eight packaging components and one store with twelve months of 2025 activity. Existing activity and supplier inputs have been retained.
Review date | Dashboard C4 is an editable snapshot date. It starts at 27-Sep-2026. Changing it updates due statuses. Legal sources were checked on 27-Sep-2026.
Current evidence | All five supplier claims remain Unverified. Descriptions such as technical sheet received are synthetic scenario text; no actual supplier documents were provided.
Evidence readiness | Suppliers V4 counts records ready for approval divided by all supplier records. A claim needs verification, a real reference and current evidence before it is ready for a wording review.
Weight data completion | Packaging R4 counts component rows with usable keys, material, component, weight and volume. Completeness does not mean that weights are verified.
Recycled material | Verified recycled percentages stay blank until evidence confirms the percentage, packaging components and material source. Zero would mean a known absence of recycled content.
Monthly calculations | Energy use multiplied by the relevant kg CO2/kWh factor gives kg CO2. Annual recycling is recycled waste divided by total waste over the same year.
Emissions boundary | Current outputs are energy-related CO2 estimates. A full greenhouse-gas inventory needs a boundary, further sources and gases, and an appropriate electricity accounting method.
Legal register | Six screening topics are included for the sample products. Source dates, conditional application dates and internal tasks are kept separate. Scope and readiness require review.
Costs | Quantity multiplied by rate gives base cost. A shared 10% planning contingency is added. Staff time is included as a resource cost. Actual amounts are unknown.
How to update | Edit amber cells. Formula cells are pale green. Use dropdown values. Keep IDs unique. Record an evidence reference before changing a verification or closure decision.
Adding records | Add records inside the relevant Excel Table and fill its formulas. Supplier, product and packaging lookups/summaries allow rows 2 to 501. Extend fixed action, cost and monthly ranges when their record counts change.
Date handling | Dates are numeric Excel dates displayed as dd-mmm-yyyy or mmm-yyyy. Supplier requests dated 28-Sep-2026 show Scheduled when reviewed on 27-Sep-2026.
Action closure | A Closed status requires a completion date and a closure evidence reference. Supplier action fields read Suppliers, so update the source instead of overwriting links.
Theme | Forest green #245B36; leaf green #6D963D; pale green #EAF2E8; amber inputs #FFF2CC; red exceptions #FBE7E5. Arial provides a consistent font across cells and charts.
Further explanation | See ESG_Project_Walkthrough.docx for the build steps, formulas, sources, dashboard choices, testing and interview preparation.